## Sheet1
Task | Description | Critical level | Deadline | R | A | C | I
Team Assembly | Hiring specialized mechanical and remote handling engineers | Medium | 2026-01-31 | Faiz Shaikh | Simulation & Structural Analyst | Colleagues | All
ITER Review | Literature review of ITER blanket remote handling systems | Low | 2026-02-15 | Faiz Shaikh | Simulation & Structural Analyst | Colleagues | All
Specs Definition | Establish the exact physical parameters the machine must handle | High | 2026-02-28 | Faiz Sahikh | Mechanical Design Engineer | Colleagues | All
Rad-Hard Analysis | Analysis of radiation shielding and material compatibility requirements | High | 2026-02-28 | Simulation & Structural Analyst | Faiz Shaikh | Colleagues | All
Design of the machine concept 1 | One of the two preliminary versions of the concept design being developed in parllel | Low | 2026-03-21 | Mechanical Design Engineer | Faiz Shaikh | Colleagues | All
Design of the machine concept 2 | One of the two preliminary versions of the concept design being developed in parllel | Low | 2026-03-21 | Mechanical Design Engineer | Faiz Shaikh | Colleagues | All
Failure Analysis | Identify potential critical failures for each lifting design approach | Medium | 2026-04-10 | Simulation & Structural Analyst | Faiz Shaikh | Colleagues | All
Trade-off Study | Selection of final lifting concept via weighted criteria | High | 2026-04-22 | Mechanical Design Engineer | Faiz Shaikh | Colleagues | All
CAD Modeling | 3D modeling of the selected concept in SolidWorks | Medium | 2026-06-15 | Mechanical Design Engineer | Faiz Shaikh | Colleagues | All
FEA Simulation | Structural Finite Element Analysis using ANSYS | High | 2026-07-10 | Simulation & Structural Analyst | Faiz Shaikh | Colleagues | All
Path Planning | Kinematic simulation of lifting trajectory using DELMIA | High | 2026-07-20 | Simulation & Structural Analyst | Faiz Shaikh | Colleagues | All
Rad-Hard Sourcing | Selection of radiation-hardened hydraulic and electronic components | Medium | 2026-07-31 | Robotics Technician | Faiz Shaikh | Colleagues | All
Procurement | Order long-lead materials required for the machine's primary frame | Low | 2026-08-31 | Faiz Sahikh | Mechanical Design Engineer | Colleagues | All
Frame Fabrication | Manufacturing of the primary structural support frame | Medium | 2026-10-20 | Robotics Technician | Faiz Shaikh | Colleagues | All
Systems Integration | Integration of the control system and sensors | Medium | 2026-10-31 | Robotics Technician | Faiz Shaikh | Colleagues | All
Prototyping | Prototype manufacturing | Low | 2026-10-31 | Robotics Technician | Faiz Shaikh | Colleagues | All
Load Testing | Test lifting capacity using weights | Medium | 2026-11-25 | Robotics Technician | Faiz Shaikh | Colleagues | All
Control Validation | Validation of remote control latency and positioning accuracy | High | 2026-12-10 | Robotics Technician | Faiz Shaikh | Colleagues | All
Compliance | Final safety certification and radiation resistance documentation | High | 2026-12-24 | Simulation & Structural Analyst | Faiz Shaikh | Colleagues | All
Site Deployment | Delivery and on-site assembly at the CFETR facility | Low | 2027-01-13 | Robotics Technician | Faiz Shaikh | Colleagues | All